## Slide 1
ePTW SYSTEM REBUILD
Proposal for a controlled, secure and maintainable Permit-to-Work platform
Prepared for solution alignment and implementation planning
September 2026
Notes: Purpose: present the rebuild direction and obtain approval to proceed into requirements closure and production data profiling.
Sources:
- OST PPT Template Apr 2026.potx

## Slide 2
01
Executive proposal
Approval requested for the rebuild direction, with policy decisions closed before schema freeze
RECOMMENDATION
Rebuild ePTW around one controlled permit domain, a server-enforced workflow and a PostgreSQL system of record.
Business outcome
A consistent permit journey with clearer responsibilities, stronger access control and reliable audit history.
Technical direction
React web application, dedicated API and workflow service, PostgreSQL, protected file storage and a transactional notification outbox.
Delivery approach
Freeze policy decisions, profile production data, build in increments, rehearse migration and cut over only after reconciliation gates pass.
Immediate ask: authorize requirements closure and read-only production data profiling.
Notes: The production migration recommendation remains conditional on profiling a recent sanitized production snapshot.
Sources:
- database-redesign-proposal.docx, sections 1 and 10
- ePTW-Requirements-Review.pdf, pages 5-7 and 93-95
- README.md

## Slide 3
02
Evidence base and authority order
Three sources contribute different types of evidence
01
Business requirements
95-page confirmation deck
Defines roles, user journeys, visibility, templates, closure, notifications, reporting and 16 open questions.
02
Backend redesign
PostgreSQL proposal and mapping
Defines the target domain model, 27 application tables, three migration-control tables and a phased cutover approach.
03
Frontend prototype
React and TypeScript functional draft
Demonstrates role-aware navigation, sequential approvals, linked Hot Work permits, revisions, lifecycle actions and audit views.
Recommended authority
Business requirements decide behaviour. The backend proposal decides implementation. The frontend prototype proves interaction patterns and controls, but does not define production architecture.
Prototype verification: production build succeeded and all 20 automated tests passed on 11 September 2026.
Notes: Verification run: npm.cmd run build and npm.cmd test; 3 test files and 20 tests passed.
Sources:
- ePTW-Requirements-Review.pdf
- database-redesign-proposal.docx
- old-vs-new-schema.docx
- README.md
- package.json
- tests/app.test.tsx
- tests/policy.test.ts
- tests/repository.test.ts

## Slide 4
03
Why the current platform needs a rebuild
The same defects affect safety control, data integrity and operating effort
01
Four permit shapes
Parent permits, drafts, embedded children and child permits require duplicated logic and merged reporting.
02
Approval state is implicit
Reviewer arrays and mutable group membership can change the meaning of an in-flight permit.
03
Operational data is untyped
Dates and key fields appear in several formats and template-specific answer keys.
04
History is difficult to trust
String logs and permit-shaped document copies cannot support precise filtering or reconciliation.
05
Integrity depends on application code
Numbering races, weak uniqueness and hard-coded identifiers create avoidable failure modes.
Repository inspection cannot quantify live defects. Production profiling must establish row counts, duplicates, nulls, orphaned references and historical variants.
Notes: The issues shown are code-level findings. Live prevalence remains to be measured against a sanitized production snapshot.
Sources:
- database-redesign-proposal.docx, sections 2-3
- old-vs-new-schema.docx, sections 1-3
- ePTW-Requirements-Review.pdf, pages 5-6

## Slide 5
04
Target user experience
One traceable permit journey from creation to archive
01
Create
Template-driven form, reserved fields, files and linked child permits
02
Submit
Validation completes and the company-specific approval route is fixed
03
Review
Only the current reviewer can act; reasons and signatures are recorded
04
Operate
Approved work, readings, controlled amendments and lifecycle actions
05
Close
Signed request, authorised confirmation and independent child outcomes
06
Report
Search, PDF generation, dashboards and retained audit history
Cross-cutting controls
Server-side authorization
Versioned templates and revisions
Append-only events
UTC storage with Singapore display time
Administration covers users, companies, sites, maps, disciplines, reviewer groups, templates, announcements and report access.
Notes: This slide consolidates the proposed end-to-end user journey. Specific workflow roles remain subject to the decisions on slide 9.
Sources:
- ePTW-Requirements-Review.pdf, sections 5-22
- database-redesign-proposal.docx, sections 6-8
- src/App.tsx

## Slide 6
05
Target application architecture
A dedicated service boundary moves security and workflow rules out of the browser
React web application
Role-aware navigation
Permit forms and lists
Admin and reporting views
API and workflow service
Authentication and authorization
Validation and state transitions
Approval sequencing and audit events
Search, document and report orchestration
PostgreSQL
System of record
Protected file storage
Attachments and generated output
Email delivery worker
Transactional outbox and retries
Security boundary
Read models and scheduled exports use the same canonical data and status rules as the operational API.
Notes: The current frontend stores seeded data in the browser and explicitly provides no real authentication, upload, notification or backend security.
Sources:
- database-redesign-proposal.docx, sections 4, 5 and 7
- ePTW-Requirements-Review.pdf, sections 15-21
- README.md

## Slide 7
06
Database redesign
The target model reduces duplication and makes workflow and reporting queryable
Concern | Current design | Target design
Permit storage | permits, drafts, embedded children and childpermits | One permits table; draft is a status and child is a self-reference
Workflow | Reviewer arrays and overlapping state fields | Ordered approval steps, eligible members and immutable action records
Operational fields | Mixed dates, strings and template-specific keys | Typed canonical columns; JSONB only for dynamic answers
History | Human-readable strings and permit-shaped PDF copies | Append-only events, immutable revisions and generated document links
Templates and numbering | Mutable template references and application-side counters | Pinned template versions and transactional sequences
Result: predictable filtering, reliable audit reconstruction and a migration path that preserves legacy evidence.
Notes: The proposal specifies 27 application tables and three migration-control tables.
Sources:
- database-redesign-proposal.docx, sections 3-7
- old-vs-new-schema.docx, sections 1-9

## Slide 8
07
Workflow controls proven in the prototype
The production service should retain the control intent while adopting the confirmed business chain
1
Complete permit
Required permit and safety fields must pass validation before submission.
2
Enforce current stage
Only the assigned role can act. Separation of duties blocks self-approval.
3
Record every decision
Approvals, rejection reasons, status changes and revision events remain traceable.
4
Control operational actions
Activation, suspension, resumption, closure and expiry checks use one policy layer.
5
Preserve revisions
A revised permit returns for approval and prior approved revisions become superseded.
6
Handle linked permits
Hot Work selection creates a linked child permit; final parent gating remains a policy decision.
Current prototype chain: Individual Reviewer, MT Group, Permit Manager. Requirements propose a company-driven chain with Host, Host Manager, optional stages and OPS.
Notes: The prototype is a control proof, not the final role model.
Sources:
- src/policy.ts
- src/repository.ts
- src/types.ts
- tests/policy.test.ts
- tests/repository.test.ts
- ePTW-Requirements-Review.pdf, sections 3, 8-10

## Slide 9
08
Policy decisions required before schema freeze
The supplied sources differ on six behaviours that directly affect data structures and workflow code
Decision | Requirements review | Backend or prototype position | Recommended action
Approval roles | Company-driven Host chain with optional stages | Prototype uses Individual Reviewer, MT Group and PM | Confirm one canonical role and stage model
Parent-child gating | Parent and child approval may proceed independently | Prototype blocks parent final approval until required child approval | Confirm whether approval or only work start is gated
Reviewer group changes | Changes update every live permit | Database proposal snapshots eligibility at submission | Choose audit certainty or live reassignment semantics
Template changes | Labels and ordering may change after publish | Database proposal makes published versions immutable | Version every published change and define edit rules
PDF history | Generate on demand from current state | Schema includes revisions and generated document records | Confirm retention, evidence and regeneration policy
Expiry | No dedicated Expired status proposed | Prototype contains EXPIRED and automatic expiry | Confirm status, flag and reporting behaviour
Recommendation: close these decisions in a short design authority workshop and record them as testable acceptance rules.
Notes: These are source conflicts or unresolved questions, not implementation defects in the prototype.
Sources:
- ePTW-Requirements-Review.pdf, pages 21, 35, 37-42, 56, 59, 75-76 and 83
- database-redesign-proposal.docx, sections 4-6 and 12
- src/policy.ts
- src/types.ts

## Slide 10
09
Migration and cutover approach
A restartable, evidence-preserving migration reduces operational and audit risk
0
Inventory and freeze
Profile a sanitized production snapshot. Resolve status, key mapping, numbering, retention and duplicate rules.
1
Build and rehearse
Deploy an empty PostgreSQL schema. Load reference data, users, templates and permits with deterministic mappings.
2
Reconstruct permit detail
Extract canonical fields, migrate children and retain the unmodified legacy submission in the first revision.
3
Rebuild workflow history
Recreate approval steps and events conservatively. Flag ambiguity instead of inventing historical order.
4
Synchronize and cut over
Run change capture or a short freeze, reconcile, switch traffic and retain a rollback window.
Reconciliation gates
Every source record is migrated, explicitly excluded or quarantined with a reason.
Counts reconcile by status, site, template, parent-child relationship and approval outcome.
Cutover proceeds only after critical reconciliation gates pass.
Notes: No schedule duration is asserted because the sources do not contain production volumes or resource commitments.
Sources:
- database-redesign-proposal.docx, section 10
- old-vs-new-schema.docx, section 10

## Slide 11
10
Delivery sequencing
The sequence protects domain decisions first and postpones irreversible migration work
A
Domain alignment
Close the six policy decisions, acceptance rules and role matrix.
B
Platform foundation
Authentication, authorization, schema, files, event logging and deployment pipeline.
C
Permit lifecycle
Creation, child logic, approvals, operational actions, closure and revisions.
D
Administration and reporting
Configuration screens, search, dashboards, PDF and scheduled exports.
E
Migration and launch
Profiling, ETL rehearsals, reconciliation, training, cutover and hypercare.
Each track ends with working software, automated controls and explicit exit criteria. Time and staffing estimates follow the profiling and domain-alignment work.
Notes: This is sequencing rather than a duration estimate.
Sources:
- database-redesign-proposal.docx, sections 10-11
- ePTW-Requirements-Review.pdf, sections 22-24
- README.md

## Slide 12
11
Principal delivery risks and controls
The main risks can be reduced before production migration begins
Risk | Potential impact | Primary control
Unresolved workflow policy | Schema rework and inconsistent approvals | Design authority workshop with signed acceptance rules
Unknown legacy data variants | Migration errors or incomplete history | Sanitized snapshot profiling, quarantine and reconciliation
Authorization implemented only in UI | Approval bypass or cross-company exposure | Server-side policy checks and negative security tests
Mutable configuration changes history | Past permits become difficult to explain | Versioned templates and explicit reviewer-change events
Reporting logic diverges | Dashboards disagree and trust falls | Canonical date/status definitions and shared read models
Cutover without rollback evidence | Extended operational disruption | Rehearsed cutover, rollback window and post-switch reconciliation
Risk ownership and thresholds should be assigned during implementation planning.
Notes: Risks are derived from the supplied design gaps and open questions; no probability scoring is asserted.
Sources:
- database-redesign-proposal.docx, sections 3, 10, 12 and 13
- ePTW-Requirements-Review.pdf, sections 19 and 21-24

## Slide 13
12
Decision requested
Approval now enables controlled discovery without committing to an unverified migration date
Approve the rebuild direction
PostgreSQL becomes the system of record for permits, workflow and audit history.
The React frontend continues as the interaction baseline, backed by production services and server-side controls.
Migration follows a profiled, restartable and reconciled cutover process.
Authorize next
1
Close policy decisions
Confirm roles, gating, group changes, templates, PDF history and expiry.
2
Profile production data
Use a recent sanitized snapshot and publish the reconciliation baseline.
3
Plan implementation
Assign owners, delivery capacity, environments and measurable exit criteria.
Production build and migration dates follow these three actions.
Notes: The requested decision is intentionally limited to direction and controlled discovery.
Sources:
- database-redesign-proposal.docx, sections 1, 10-12
- ePTW-Requirements-Review.pdf, pages 93-95

## Slide 14
A1
Appendix: frontend prototype coverage
The codebase demonstrates workflow intent but remains a browser-based functional draft
Demonstrated now | Production capability still required
Role-aware navigation and permit queues | Real identity provider integration, sessions and server authorization
Template-driven permit creation and validation | Published template versioning, reserved-field enforcement and file services
Sequential review decisions and separation of duties | Confirmed role chain, delegation policy, concurrency and transactional workflow
Linked Hot Work child permit and parent controls | Full B1-B5/LSS rules, merge semantics and decision on approval gating
Activation, suspension, closure, expiry and revisions | Confirmed status model, notifications, scheduled jobs and immutable history
Admin screens for users, sites, maps, templates and groups | Persistent master data, soft deletion, audit logging and permission checks
Local search, audit register and PDF action placeholders | Server-side search, dashboards, exports, document generation and storage
Verification: React production build succeeded; 3 test files and 20 tests passed.
Notes: The README explicitly states that the draft has no real authentication, file upload, notification or backend security.
Sources:
- README.md
- src/App.tsx
- src/TemplateBuilderPage.tsx
- src/AdminUsersMaps.tsx
- src/AdminDirectories.tsx
- src/policy.ts
- src/repository.ts
- tests/*.ts and tests/*.tsx